## Project schedule
| CDE Classification | [5 empty] | Project start: | [7 empty] | 2023-09-04
| Project manager: | Muhammad Zariff Wafiy |  |  |  |  | Display week: | [7 empty] | 1
[7 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25 | [6 empty] | 2023-10-02 | [6 empty] | 2023-10-09 | [6 empty] | 2023-10-16 | [6 empty] | 2023-10-23
| TASK |  | PROGRESS | START | END | time axis 2023-09-04 to 2023-10-29
 | time axis 2023-09-04 to 2023-10-29
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
1. Initiation / preparation
| 1.1. Briefing of CDE Project |  | 100% | 2023-09-04 | 2023-09-05 | 2
| 1.2. CDE concept familiarization |  | 100% | 2023-09-05 | 2023-09-10 | 6
| 1.3. Tools identification and installation |  | 100% | 2023-09-10 | 2023-09-12 | 3
| 1.4. Identify business pain points |  | 100% | 2023-09-12 | 2023-09-14 | 3
| 1.5. Identify and interview personas |  | 100% | 2023-09-14 | 2023-09-17
| 1.6. Determine project objectives |  | 100% | 2023-09-17 | 2023-09-19
| 1.7. Identify possible workspaces for Python codes |  | 100% | 2023-09-19 | 2023-09-21
b | 1.8. Get familiar with Azure Cognitive Services |  | 100% | 2023-09-21 | 2023-09-26
| 1.9. Prepare project proposal slides |  | 100% | 2023-09-26 | 2023-10-25 | 30
2. Planning and design
| 2.1. Design flow diagram |  | 100% | 2023-09-20 | 2023-09-25 | 6
| 2.2. Ideation of possible solution |  | 100% | 2023-09-25 | 2023-09-30 | 6
| 2.3. Identify possible algorithms |  | 100% | 2023-09-30 | 2023-10-07 | 8
| 2.4. Sample code for soft cosine similarity |  | 100% | 2023-09-30 | 2023-10-03 | 4
| 2.5. Sample code for fuzzy logic and BERT |  | 100% | 2023-10-01 | 2023-10-05
| 2.6. Confirm a possible output format (API) |  | 100% | 2023-10-03 | 2023-10-07
| 2.7. Identify data types in data dictionary |  | 100% | 2023-10-07 | 2023-10-08 | 2
| 2.8. Presentation of proposal to HOD |  | 100% | 2023-10-25 | 2023-10-25 | 1
3. Execution
| 3.1. Exploratory Data Analysis |  | 100% | 2023-10-25 | 2023-10-30 | 6
| 3.2. Data cleaning |  | 100% | 2023-10-30 | 2023-11-04 | 6
| 3.3. Feature Engineering |  | 100% | 2023-11-04 | 2023-11-09 | 6
| 3.4. Develop model A |  | 100% | 2023-11-09 | 2023-11-19 | 11
| 3.5. Test and Evaluation model A |  | 100% | 2023-11-19 | 2023-11-29 | 11
| 3.6. Develop model B |  | 100% | 2023-11-29 | 2023-12-09 | 11
| 3.7. Test and Evaluation model B |  | 100% | 2023-12-09 | 2023-12-19 | 11
| 3.8. Develop model C |  | 100% | 2023-12-19 | 2023-12-29 | 11
| 3.9. Test and Evaluation model C |  | 100% | 2023-12-29 | 2024-01-08 | 11
| 3.10. Validation |  | 100% | 2023-11-19 | 2023-11-23 | 5
4. Evaluation
| 4.1. Develop prototype |  | 100% | 2023-10-27 | 2023-10-30 | 4
| 4.2. Deploy prototype to production |  | 0% | 2023-10-30 | 2023-11-03 | 5
| 4.3. User testing |  | 0% | 2023-11-03 | 2023-11-07 | 5
Formulas:
Display week: = [Display week:, row below]